## Risk Register
RISK ASSESSMENT REGISTER
Log each hazard/risk below. Enter Likelihood and Severity (1-5) using the dropdowns; Risk Score and Risk Level calculate automatically. See the Definitions tab for rating criteria and the Risk Matrix tab for the live heat map.
Risk ID | Date Identified | Department / Area | Hazard / Risk Description | Likelihood (1-5) | Severity (1-5) | Risk Score | Risk Level | Existing Controls | Additional Controls Needed | Risk Owner | Target Completion Date | Status | Date Last Reviewed | Notes | Low X | Low Y | Medium X | Medium Y | High X | High Y | Critical X | Critical Y
R-001 | EXAMPLE | Warehouse | Forklift travel paths cross pedestrian walkway | 3 | 4 | 12 | High | Painted floor lines; convex mirrors at blind corners | Install physical barrier or pedestrian gate | Warehouse Supervisor |  | Open | [6 empty] | 3 | 4
R-002 | EXAMPLE | Maintenance Shop | Compressed gas cylinders stored without secure restraint | 2 | 3 | 6 | Medium | Cylinders capped when not in use | Install wall-mounted cylinder racks with chains | EHS Coordinator |  | In Progress |  |  |  |  | 2 | 3
R-003 | EXAMPLE | Lab | Incompatible chemicals stored on same shelf | 2 | 5 | 10 | High | SDS on file for all chemicals | Segregate per compatibility chart; add secondary containment | Lab Manager |  | Open | [6 empty] | 2 | 5
R-004
R-005
R-006
R-007
R-008
R-009
R-010
R-011
R-012
R-013
R-014
R-015
R-016
R-017
R-018
R-019
R-020
R-021
R-022
R-023
R-024
R-025
R-026
R-027
R-028
R-029
R-030
R-031
R-032
R-033
R-034
R-035
R-036
R-037
R-038
R-039
R-040
R-041
R-042
R-043
R-044
R-045
R-046
R-047
R-048
R-049
R-050

## Risk Matrix
RISK MATRIX - LIVE HEAT MAP
Each cell shows the count of risks currently logged in the Risk Register at that Likelihood / Severity combination. Counts update automatically as you edit the register.
LIKELIHOOD
|  | 1 | 2 | 3 | 4 | 5
SEVERITY | 5 |  | R-003
| 4 |  |  | R-001
| 3 |  | R-002
2
1
1 = Rare / Negligible 5 = Almost Certain / Catastrophic - see Definitions tab
LEGEND
Level | Score Range | Suggested Response
Low | 1-4 | Acceptable with routine monitoring; no immediate action required.
Medium | 5-9 | Address with planned corrective action; reassess on a routine schedule.
High | 10-15 | Prioritize corrective action; assign an owner and target date promptly.
Critical | 16-25 | Stop the activity or implement immediate interim controls; escalate to leadership.

## Definitions
RATING DEFINITIONS
Use these criteria consistently when rating Likelihood and Severity in the Risk Register. Adjust wording to fit your operation, but keep the 1-5 scale intact so the matrix and formulas continue to work.
LIKELIHOOD - how often could this occur?
Rating | Term | Description
1 | Rare | Conceivable but not expected to occur during the life of the operation; no known history of occurrence.
2 | Unlikely | Could occur at some point; has happened rarely in similar operations.
3 | Possible | Might occur occasionally; has happened before in this operation or similar ones.
4 | Likely | Will probably occur in most circumstances; has happened more than once here.
5 | Almost Certain | Expected to occur in most circumstances; happens regularly or is ongoing.
SEVERITY - how bad could the outcome be?
Rating | Term | Description
1 | Negligible | No injury or first-aid only; no environmental release; minimal or no cost impact.
2 | Minor | Minor injury with no lost time; small reportable spill fully contained on site; low cost impact.
3 | Moderate | Injury requiring medical treatment or lost work time; reportable release requiring agency notification; moderate cost impact.
4 | Major | Serious injury, hospitalization, or permanent impairment; significant environmental release; major regulatory citation or cost impact.
5 | Catastrophic | Fatality or multiple serious injuries; major environmental damage; facility shutdown, criminal liability, or severe financial impact.
RISK LEVEL BANDS (Risk Score = Likelihood x Severity)
Level | Score Range | Meaning
Low | 1-4 | Acceptable; manage with routine procedures.
Medium | 5-9 | Tolerable; plan and schedule corrective action.
High | 10-15 | Significant; prioritize corrective action and assign an owner.
Critical | 16-25 | Unacceptable; take immediate interim action and escalate.

## Regulatory Reference
REGULATORY REFERENCE
This tool supports, but does not replace, a documented risk/hazard assessment program. Verify current requirements with the citing agency or standards body.
Standard | Citation | Relevance to Risk Assessment
OSH Act - General Duty Clause | Sec. 5(a)(1) | Requires employers to furnish a workplace free from recognized hazards; documented risk ranking supports demonstrating hazard recognition and reasonable abatement priority.
OSHA - PPE Hazard Assessment | 29 CFR 1910.132(d) | Requires employers to assess the workplace for hazards and certify the assessment; a risk register documents this evaluation.
OSHA - Process Safety Management | 29 CFR 1910.119 | Requires a process hazard analysis that includes a risk-ranking methodology for covered processes.
OSHA - HazCom | 29 CFR 1910.1200 | SDS and label hazard information feed the Severity rating for chemical-related risks.
ANSI/ASSP Z690.3 | Z690.3-2011 (R2021) | National guidance on selecting and applying risk assessment techniques, including risk matrices.
ANSI/ASSP Z10 | Z10-2019 | Occupational health and safety management systems standard requiring a documented hazard identification and risk assessment process.
ISO 31000 | ISO 31000:2018 | International risk management guidelines referenced for risk evaluation criteria and treatment prioritization.